## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Aakash | Write a program for displaying the home page | 1 | [6 empty] | Closed | bar: New Estimates of Effort remaining at end of Day1
|  | Task 2 | Aakash | Design the UI for the Home page | 1 | [6 empty] | Closed | bar: New Estimates of Effort remaining at end of Day1
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the home page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5
US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Aakash | Write a program for displaying the create customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the create Customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the create customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Aakash | Write a program for displaying the edit customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the edit Customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the edit customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Aakash | Write a program for displaying the delete customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the delete Customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the delete customer page | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day1: 0.5 | Closed
US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Aakash | Write a program for displaying the status customer page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the status Customer page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the status customer page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Aakash | Write a program for displaying the create account page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the create account page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the create page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
US007 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Aakash | Write a program for displaying the delete account page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the delete account page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the delete account page | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day2: 0.5 | Closed
US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Aakash | Write a program for displaying the status account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the status account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the status account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
US009 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Aakash | Write a program for displaying the search customer page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the search customer page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the search customer page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
US010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Aakash | Write a program for displaying the search account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the search account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the search account page | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day3: 0.5 | Closed
US011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Aakash | Write a program for displaying the deposite money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the deposite money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the deposite money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
US012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Aakash | Write a program for displaying the withdraw money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the withdraw money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the deposite money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
US013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Aakash | Write a program for displaying the transfer money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the transfer money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the transfer money page | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day4: 0.5 | Closed
US014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Aakash | Write a program for displaying the account statement page | 0.5 | New Estimates of Effort remaining at end of Day5: 0.5 | Closed
|  | Task 2 | Aakash | Design the UI for the account statement page | 0.5 | New Estimates of Effort remaining at end of Day5: 0.5 | Closed
|  | Task 3 | Aakash | Design and create the DB fields | 0.5 | New Estimates of Effort remaining at end of Day5: 0.5 | Closed
|  | Task 4 | Aakash | Write test conditions to test the account statement page | 0.5 | New Estimates of Effort remaining at end of Day5: 0.5 | Closed
|  | Task 5 | Aakash | Execute the tests | 0.5 | New Estimates of Effort remaining at end of Day5: 0.5 | Closed
[5 empty] | 36 | 11 | 7.5 | 7.5 | 7.5 | 2.5 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
11 | 7.5 | 7.5 | 7.5 | 2.5 | 0 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0